## GanttChart
[网页爬虫：诗词宝典+书法词典] 项目进程管理
[小组成员] 何杨林 季薇璐
| 项目开始日期 | 2018-11-06 | [5 empty] | 显示周 | 7 |  | 第1周 | [6 empty] | 第2周 | [6 empty] | 第3周 | [6 empty] | 第4周 | [6 empty] | 第5周
[11 empty] | 2018-12-17 | [6 empty] | 2018-12-24 | [6 empty] | 2018-12-31 | [6 empty] | 2019-01-07 | [6 empty] | 2019-01-14 | [6 empty] | 2019-01-21 | [6 empty] | 2019-01-28 | [6 empty] | 2019-02-04
 | time axis 2018-12-17 to 2019-02-10
项目结构 | 项目任务 | 参与人 | PREDECESSOR | 开始时间 | 结束时间 | 时长 | 有效时长 | 完成情况 | 完成效率 | 具体说明 | time axis 2018-12-17 to 2019-02-10
1 | [前期准备]
1.1 | [任务初步分析] | 何杨林 季薇璐 |  | 2018-11-06 | 2018-11-08 | 3 | 2 | 完成 | 66.67% | 前期项目进行的效率不高，主要原因： 1. 爬虫相关了解较少 2. 材料较杂，阅读盲目 | bar: 2018-12-19
1.1.1 | [查找、阅读相关资料] | 何杨林 季薇璐 |  | 2018-11-07 | 2018-11-14 | 8 | 5 | 完成 | 62.5%
1.1.2 | [交换信息、初步讨论] | 何杨林 季薇璐 |  | 2018-11-08 | 2018-11-15 | 8 | 3 | 完成 | 37.5%
1.2 | [任务分工] | 何杨林 季薇璐 |  | 2018-11-09 | 2018-11-09 | 1 | 1 | 完成 | 100% | 初步分工：何杨林负责：前期爬虫代码阅读及单个链接爬到底；后期循环代码及保存词典部分由季薇璐负责
1.3 | [任务分工] | 徐越方洲 易可可 崔冰 余扬名 |  | 2018-02-03 | 2018-02-07 | 5 | 3 | -30810 | 50%
1.4 | [Task] |  |  | 2018-02-08 | 2018-02-11 | 4 | 2 | -30813 | 0%
1.5 | [Task] |  |  | 2018-02-01 | 2018-02-04 | 4 | 2 | -30808 | 75%
1.5.1 | [Sub-task] |  |  | 2018-02-02 | 2018-02-03 | 2 | 1 | -30810 | 50%
1.5.2 | [Sub-task] |  |  | 2018-02-04 | 2018-02-06 | 3 | 2 | -30811 | 50%
1.6 | [Task] |  |  | 2018-02-05 | 2018-02-09 | 5 | 5 | -30812 | 0%
1.7 | [Task] |  |  | 2018-02-03 | 2018-02-09 | 7 | 5 | -30810 | 0%
1.8 | [Task] |  |  | 2018-02-10 | 2018-02-16 | 7 | 5 | -30815 | 0%
2 | [书法词典]
2.1 | [对爬虫对象——国学大师网站的初步分析及探索] | 何杨林 季薇璐 |  | 2018-11-10 | 2018-11-14 | 5 | 3 | 完成 | 60%
2.2 | [浏览书法词典网页确认爬虫内容] | 何杨林 季薇璐 |  | 2018-11-10 | 2018-11-14 | 5 | 4 | 完成 | 80% | 在网页源代码中，找到对应的部分
2.3 | [阅读学习网上关于爬虫的代码及实例] | 何杨林 季薇璐 |  | 2018-11-10 | 2018-11-19 | 10 | 8 | 完成 | 80%
2.4 | [检查网页源，熟悉网页结构] | 何杨林 季薇璐 |  | 2018-11-11 | 2018-11-15 | 5 | 4 | 完成 | 80%
2.5 | [在网页源代码中检索到与任务内容相对应的部分] | 何杨林 季薇璐 |  | 2018-11-12 | 2018-11-15 | 4 | 3 | 完成 | 75%
2.6 | [撰写加载网页的代码并运行调试成功] | 何杨林 季薇璐 |  | 2018-11-20 | 2018-11-21 | 6 | 4 | 完成 | 66.67%
2.7 | [撰写爬第一层网页第一个链接的代码并运行调试成功] | 何杨林 季薇璐 |  | 2018-11-21 | 2018-11-22 | 2 | 2 | 完成 | 100% | 发现没有class名只有name名，这时候语句行不通了，无法定位到对应部分爬取。
2.7.2 | [撰写爬该链接第二层及第三层的代码并运行调试成功] | 何杨林 |  | 2018-11-22 | 2018-11-23 | 6 | 5 | 完成 | 83.33% | 最后采用Xpath的语句定位到name名
2.8 | [撰写循环部分代码爬出每个链接的完整内容并运行调试成功] | 季薇璐 |  | 2018-11-23 | 2018-11-24 | 3 | 2 | 完成 | 66.67%
2.9 | [导出并保存爬出的全部内容] | 何杨林 季薇璐 |  | 2018-11-24 | 2018-11-25 | 2 | 2 | 完成 | 100%
3 | [诗词宝典]
3.1 | [浏览诗词宝典网页确认爬虫内容] | 何杨林 季薇璐 |  | 2018-11-28 | 2018-11-28 | 1 | 1 | 完成 | 100% | 浏览网页点进每一层链接，确认爬链接+网页文字内容
3.2 | [检查网页源，熟悉网页结构] | 何杨林 |  | 2018-11-29 | 2018-11-29 | 1 | 1 | 完成 | 100% | 查看网页源代码
3.2.1 | [在网页源代码中检索到与任务内容相对应的部分] | 何杨林 |  | 2018-11-30 | 2018-12-01 | 2 | 2 | 完成 | 100% | 在网页源代码中，找到对应的部分，找到class名称
3.3 | [撰写爬第一个链接的全部三层代码并运行调试成功] | 何杨林 |  | 2018-12-01 | 2018-12-06 | 6 | 6 | 完成 | 100% | 从第一层网页的第一个诗词开始，爬出它的链接，再根据它的链接进入第二层网页，爬取网页文字内容及下一层链接和下一层文字内容 2. 学习MOSES原理
3.4 | [撰写循环部分代码爬出每个链接的完整内容并运行调试成功] | 季薇璐 |  | 2018-12-06 | 2018-12-11 | 6 | 6 | 完成 | 100%
3.5 | [导出并保存爬出的全部内容] | 季薇璐 |  | 2018-12-11 | 2018-12-15 | 1 | 1 | 完成 | 100%
4 | [Task Category]
4.1 | [Task] |  |  | 2018-01-29 | 2018-01-29 | 1 | 1 | -30806 | 0%
4.2 | [Task] |  |  | 2018-01-30 | 2018-01-30 | 1 | 1 | -30807 | 0%
4.3 | [Task] |  |  | 2018-01-31 | 2018-01-31 | 1 | 1 | -30808 | 0%
4.4 | [Task] |  |  | 2018-02-01 | 2018-02-01 | 1 | 1 | -30809 | 0%
4.5 | [Task] |  |  | 2018-02-02 | 2018-02-02 | 1 | 1 | -30810 | 0%
[7 empty] | - | -
[7 empty] | - | -
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
1 | [ Level 1 Task or Phase ] |  |  |  | - |  | - | -
1.1 | . [ Level 2 Task ] |  |  |  | - |  | - | -
1.1.1 | . . [ Level 3 Task ] |  |  |  | - |  | - | -
1.1.1.1 | . . . [ Level 4 Task ] |  |  |  | - |  | - | -
4 | [后期准备]
4.1 | [总结整理问题与解决方法] | 何杨林 季薇璐 |  | 2018-12-20 | 2018-12-20 | 5 | 4 | 完成 | 80%
4.2 | [撰写汇报PPT] | 季薇璐 |  | 2018-12-25 | 2018-12-26 | 2 | 2 | 完成 | 100% | 1.报告以ppt的形式呈现
4.3 | [撰写项目管理表格] | 何杨林 |  | 2018-12-24 | 2018-12-26 | 2 | 2 | 完成 | 100% | 2.报告分为两个部分。第二部分为本项目管理表格
5 | [最后优化]
5.1 | [整理注释代码、调试] | 何杨林 季薇璐 |  | 2018-12-25 | 2018-12-26 | 2 | 2 | 完成 | 100%
Formulas:
第1周 = [第1周, row below]
第2周 = [第2周, row below]
第3周 = [第3周, row below]
第4周 = [第4周, row below]
第5周 = [第5周, row below]
Note on A7: 项目基本架构 Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, …
Note on B7: 项目任务 项目任务基本描述
Note on C7: 参与人 项目任务的对应参与人/负责人
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: 开始时间 该任务的开始时间
Note on F7: 结束时间 该任务的真实结束时间
Note on G7: 时长 该任务持续的时长，由结束时间减去开始时间
Note on H7: 有效时长 完成该任务的有效时长，即真实工作时长
Note on I7: 完成情况 是否完成任务
Note on J7: 完成效率: 有效时长/时长
Note on K7: 具体说明 对任务细节的具体说明，如：具体分工、具体解决的内容、遇到的问题等

## GanttChartPro
Gantt Chart Template Pro
Gantt Chart Template Pro is similar to this free version, but
it is more feature-packed. It also comes with other bonus content.
Learn About Gantt Chart Template Pro
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
The following link is a blog post that talks specifically about the
Pro version for Excel Online.
Gantt Chart Template Pro for Excel Online
Benefits and Features of Gantt Chart Template Pro
Simple Color-Coding
The Pro version includes a column for specifying the color of bars in the chart. For example,
you could change the color based on urgency or task lead.
Daily, Weekly, or Monthly View
The Pro version includes a drop-down next to the Display Week that lets you choose to display
the columns in the chart area as days, weeks, or months.
Use Work Days as an Input
By default, the Pro version is set up to have you enter Work Days instead of Calendar Days.
The expanded set of template rows provides more options for defining the Start date, End date,
and Duration of tasks. Define a task based on …
- Start date and End date
- Start date and Work days
- Start date and Calendar days
Easily Create Task Dependencies
Though you can still use your own formulas for creating task dependencies, the Pro version
includes template rows that calculate the Start date based on the WBS number that you enter
in the Predecessor column.
Exclude Holidays from Work Days
List holidays and other specific non-working days that you want to exclude from work days.
Customize Your Work Week
The versions designed for Excel 2010+ use the WORKDAY.INTL() and NETWORKDAYS.INTL()
functions that allow you define the work week as something other than Monday-Friday.
Learn More About Gantt Chart Template Pro

## Help
Help
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
About This Template
This Gantt Chart Template provides an easy way to create a simple project schedule. You only need to know some basic spreadsheet operations, such as how to insert, delete, copy and paste rows and cells. For more advanced uses, such as defining task dependencies, you will need to know how to enter formulas.
Be sure to read the Getting Started Tips below. Watching the video demos for Gantt Chart Template Pro may also help you see how to use the spreadsheet.
Watch Demo Videos of the Pro Version on Vertex42.com
Please read the license agreement in the TermsOfUse worksheet to learn how you may or may not use and share this spreadsheet.
Getting Started Tips
• [Bracketed Text] is meant to be edited, like the project title and task descriptions.
| • Some of the labels include cell comments to provide extra information. | Label
• To adjust the range of dates shown in the Gantt chart, change the Display Week number.
• The Project Start Date is used to define the first week shown in the gantt chart.
• Insert new tasks using one of the methods listed below.
| • Define the task start date and duration (days) by editing the light green cells. | Input Cell
• If you see "#####" in a cell, widen the column to display the cell contents.
• Backup your file regularly to avoid losing data! Excel files get corrupted occasionally.
Inserting New Tasks (Rows)
When inserting and deleting tasks, you need to insert and delete entire rows. Some columns contain formulas (such as the End Date and the Work Days columns), so these formulas need to copied to the newly inserted rows.
METHOD 1 (recommended)
• Insert a new blank row by right-clicking on the row number and selecting Insert.
• With the new blank row selected, press Ctrl+d to copy the formulas and formatting down from the row above OR use the row drag handle to copy the formulas and formatting down.
METHOD 2
• Copy a row from the set of template rows at the bottom of the worksheet.
• Right-click on the row where you want to insert the new task and select Insert Copied Cells.
Method 2 will work, but Excel will split/fracture/duplicate conditional formatting rules rather than merging the rules. This can cause inefficiencies in very large and heavily modified files.
Help improve Excel by voting on a suggestion to fix this problem.
Using the Template Rows and Choosing a WBS Level
The set of template rows at the bottom of the Gantt Chart worksheet provide examples of different ways to format and define tasks for different WBS levels.
Each different WBS level uses a different formula in the WBS column.
You can either copy/paste/insert these template rows via Method 2 as explained above, OR you can just copy/paste the desired WBS cell when you want to change the WBS level.
If you leave a blank cell above a WBS number, the numbering will reset to 1.x.x. The formulas are meant for convenience, but you can manually enter the WBS numbers if you want to.
You can indent the task description for sub-tasks by entering leading spaces or using the Indent feature in Excel.
Creating Task Dependencies
You can enter the Start date manually, or define task dependencies using a formula. Below are some common options for defining the Start date:
A. | Enter the date manually (e.g. 1/3/2015)
B. | Reference the Project Start Date (e.g. =$E$4 )
C. | Set the Start date to the next Work Day after another task's End date.
• Use the formula =WORKDAY(enddate,1) where enddate is the reference to the End date of a predecessor task.
• For multiple predecessors, the formula would be =MAX(WORKDAY(enddate1,1),WORKDAY(enddate2,1))
D. | Set the Start date to the next Calendar Day after another task's End date.
• This formula is very simple: =enddate+1
• For multiple predecessors, the formula would be =MAX(enddate1,enddate2,enddate3)+1
E. | Set the Start date to a number of days before or after another date.
• This formula is just like the one in C or D, except that in place of the "1" you enter the number of days, such as =WORKDAY(enddate,5) or =WORKDAY(startdate,-5)
F. | Use a lookup formula and the Predecessor column to define the start date.
[The formulas for using this method are built into Gantt Chart Template Pro]
Changing the Color of the Bars in the Gantt Chart
[Advanced] The Gantt Chart is created using conditional formatting, so you can modify the conditional formatting rules to change the format to a different color. The Pro version includes a column where you can change the color by entering a color code ("b"=blue, "g"=green, etc.)
FAQs
Q: | How do I enter the Work Days instead of Calendar Days?
Entering work days instead of calendar days is a feature of the Pro version. There is nothing in the free version preventing you from entering your own formulas, though.
Q: | How do I calculate Calendar Days after entering the Start and End Dates?
You can calculate the duration in calendar days (including both start and end dates) using the formula =enddate-startdate+1
Q: | How do I change the Print Settings? (Excel 2010, 2013)
Select the entire range of cells you want to print and go to File > Print Area > Set Print Area. Then go to File > Page Setup or File > Print Preview and adjust the Scaling, Margins, and Page Orientation as desired.
Q: | How do I increase the range of dates displayed in the Gantt chart?
You will need to add columns to the right of the Gantt Chart via copy/paste. Copy and paste the columns in groups of 7. Afterwards, you will also probably need to update the print area.
Q: | How do I create a summary row that shows the MIN and MAX dates for all sub-tasks?
In the Start column, use the formula =MIN(range_of_start_dates)
In the End column, use the formula =MAX(range_of_end_dates)
In the Days column, use the formula =end_date-start_date+1
Q: | How do I calculate the %Complete for an entire category of tasks?
The %Complete for a group of tasks can be calculated from its sub tasks using the formula below, where "workdays" is a reference to the range of work day values and "complete" is a reference to the %complete for each of the subtasks.
=SUMPRODUCT(workdays,complete)/SUM(workdays)
Example: Let's say you have 3 sub tasks that are 10 days, 12 days, and 14 days long, respectively. If the first subtask is 50% complete and the others are 25% complete, you could calculate the overall percent complete for the group as: =(10*50%+12*25%+14*25%)/(10+12+14).
Q: | I've messed up the chart area somehow. How do I fix it?
Find a row that works, then copy the cells that make up the gantt chart area from that row into the row that is messed up.
© 2006-2018 Vertex42 LLC
Note on C16: This is an example comment.

## TermsOfUse
Terms of Use
Gantt Chart Template, by Vertex42.com
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
© 2006-2018 Vertex42 LLC
This spreadsheet template, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
You may download the spreadsheet template, make archival copies, and customize the template only for your personal use or use within your company or organization and not for resale or public sharing.
You may not remove or alter any Vertex42 logo, trademark, copyright, disclaimer, brand, terms of use, attribution, or other proprietary notices or marks within the template.
The template and any file, document, or other work including or derived from the template may NOT be sold, distributed, published to an online gallery, hosted on a website, or placed on any server in a way that makes it available to the general public.
Limited Private Sharing and Other Allowed Uses: See the complete license agreement to learn more about how you may or may not use this template.
View the Complete License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html